## Photosensors
Mar 2021 | Readout Electronics Timeline Estimate | 2021 |  | 2022 |  | 2023 |  | 2024
|  |  | FY22 |  | FY23 |  | FY24
Simulation/Reconstruction | Simulation: Prototype, beam line, cosmic ray setup (CRT)
Simulation: Lens characterization
Simulation: Explore hpDIRC design options (e/π,π/K)
Simulation: Cost/performance optimization
Reconstruction: reconstruction optimization / ML
hpDIRC system prototype | Transfer of PANDA prototype from GSI to CUA/SBU
Design and construction of CRT
Initial protoype commissioning in cosmic ray setup (CRT)
Upgrade of sensors and readout electronics
Commissioning of upgraded prototype, CRT data analysis
Optional beam test at Fermilab
Beam test data analysis
ToT based readout | Reference readout based on MAROC3 (F/E) + SSP (DAQ)
Validation of ALCOR architecture (1st production samples)
Basic readout chain from ALCOR+ARCADIA developments
Develop a portable DAQ system
Test of streaming readout
Upgraded ALCOR readout chain for dRICH
Submission of a custom ALCOR design
Optimize ALCOR with proper signal preconditioning
Integration of SiPM readout with sensor cooling
Engineering of SiPM readout and services
Sensors and Electronics | collaboration effort within eRD14
TDR

## Electronics
Mar 2021 | Electronics Timeline Estimate | 2021 |  | 2022 |  | 2023 |  | 2024
|  |  | FY22 |  | FY23 |  | FY24
Si-READ | Firmware completion
Configuration scripts
Acquisition software
Data Taking
Documentation of performance
HDSoC | 32-channel evaluation
64-channel design
64-channel evaluation
1k readout demonstrator (mRICH)
hpDIRC
LAPPD Gen III
WBS system costing
Lens evaluation | Upgrade of ODU laser setup
Characterization of prototype lenses
Neutron irradiation and analysis
BaBar DIRC bar reuse | Plan, preparation
Bar box disassembly, bar decoupling
Validate mechanical and optical properties
Sensors and Electronics | collaboration effort within eRD14
TDR