## Photosensors
_
| Mar 2021 | Photosensors Timeline Estimate | 2021 |  | 2022 |  | 2023 |  | 2024
|  |  |  | FY22 |  | FY23 |  | FY24
| High-B Sensor Program | Scan of 10-μm XP85122-S, HiCE Planacon
Scan of 6-μm Photek MCP PMT, MAPMT253
Full-area uniformity scan with UH electronics
Incom GEN-III (HRPPD) scan
| MCP-PMT/LAPPD | Beamline test of MCP-PMT/LAPPD with pixel readout
mRICH-LAPPD-ToF experiment with Gen-II LAPPD
Magnetic field test of LAPPD prototypes
Fabrication of 10x10 cm MCP-PMT for prototype validation
Bench evaluation of MCP-PMT, LAPPD and HRPPD
Integration of UHawaii electronics with available sensors
Beamline evaluation of RICH subsystems with available MCP-PMT/LAPPD
| SiPM program | Status-of-the-art sensor selection
Irradiation and temperature treatment (standard sensors)
Post-irradiation response with dedicated readout
Custom sensor solutions (with manufacturers )
Irradiation and temperature treatment (custom sensors)
Engineering of cooling and services
| Sensors and Electronics | collaboration effort within eRD14
TDR

## Electronics
Mar 2021 | Electronics Timeline Estimate | 2021 |  | 2022 |  | 2023 |  | 2024
|  |  | FY22 |  | FY23 |  | FY24
Si-READ | Firmware completion
Configuration scripts
Acquisition software
Data Taking
Documentation of performance
HDSoC | 32-channel evaluation
64-channel design
64-channel evaluation
1k readout demonstrator (mRICH)
hpDIRC
LAPPD Gen III
WBS system costing
Lens evaluation | Upgrade of ODU laser setup
Characterization of prototype lenses
Neutron irradiation and analysis
BaBar DIRC bar reuse | Plan, preparation
Bar box disassembly, bar decoupling
Validate mechanical and optical properties
Sensors and Electronics | collaboration effort within eRD14
TDR