## DIRC
Mar 2021 | dRICH Timeline Estimate | 2021 |  | 2022 |  | 2023 |  | 2024
|  |  | FY22 |  | FY23 |  | FY24
Simulation/Reconstruction | Simulation: Prototype and beam line
Simulation: Integration into EIC simulation and analysis platforms
Simulation: dRICH model refinement with the beam-test results
Simulation: dRICH model optimization in EIC spectrometer
Reconstruction: reconstruction optimization / ML
dRICH Prototype | Basic prototype design
Basic prototype mechanics
Basic tracking and components, reference readout
Upgrade of sensors and readout electronics
Precise tracking/alignment
Custom components, optimized readout
Beam test data analysis
Optical Components | First selection and tests
Refinement and cost reduction study
Alternatives and optimization
Beam-Tests | Proof of principle (reference sensors and readout, ideal beam)
Performance assessment (hadron tagged beams)
Performance assessment with optimized components
EIC Integration | Cooling R&D
EIC configuration engineering and integrated PID
Engineering of cooling and ancillary services
TDR