## Slide 1
dRICH Timeline
Year | Detailed tasks
2021 | Development of basic prototype design, simulation and implementation Optical components: First selection and tests Basic prototype: Basic tracking, one choice per radiator, glass mirrors, reference readout Beam Test 1: Proof of principle with reference detectors and readout , ideal beam Import dRICH simulation into the supported EIC platforms
2022 | Analysis of the first test-beam Refined prototype: refined components and readout, online reconstruction, precise tracking/alignment Beam Test 2: Performance assessment with reference and custom detectors, hadron tagged beams
2023 | R&D on cooling EIC configuration engineering and integrated PID Optical components refinement and cost reduction study (e.g. glass-skin mirror
2024 | Component alternatives and optimization Final prototype: various radiators, custom mirrors, gas system, optimized readout Beam test 3: Performance assessment with optimized components
2025 | Engineering of cooling and services Beam test 4: Contingency

## Slide 2
Photosensor Timeline
Year | Detailed tasks
2021 | SiPM program: radiation tolerance with temperature treatment of status-of-the-art sensor selection
2022 | SiPM program: study of post-irradiation response with dedicated readout electronics SiPM program: work with manufacturers to implement custom solutions
2023 | SiPM program: radiation tolerance and temperature treatment of custom sensors SiPM program: work with manufacturers to implement optimized solutions
2024 | SiPM program: radiation tolerance and cooling program of optimized sensors
2025 | SiPM program: engineering of cooling and services

## Slide 3
Readout Timeline
Year | Detailed tasks
2021 | Maintain reference readout based on MAROC3 (F/E) + SSP (DAQ) Test present version of ALCOR chip (spare samples from first batch production) Develop a basic readout chain based on ALCOR + ARCADIA INFN developments
2022 | Update ALCOR and ARCADIA readout chain to meet dRICH requirements Submission of a custom ALCOR design Develop a portable DAQ system
2023 | Optimize ALCOR with proper signal preconditioning Submission of the optimized ALCOR design
2024 | Integration of SiPM readout with sensor cooling
2025 | Engineering of SiPM readout and services

## Slide 4
TDR Readiness
2020
Prototype design,
simulation and
implementation
Basic mechanics
Electronics
adaptation
Component test
and selection
Start of INFN funds
2021
Basic prototype
- basic tracking
- 1 radiator choice
- commercial mirror
- reference readout
Beam Test 1
- MA-PMTs, SiPMs
- Pion beam
- Critical aspects
Optical components
test and selection
SiPM program
radiation tolerance
and cooling program
Status-of-the-art
2022 ++
Refined prototype
- precise tracking/alignment
- various radiators
- custom mirrors
- gas system
- optimized readout
- online reconstruction
Beam Test 2
- MCP-PMTs, SiPMs
- Hadron beam
- Performance optimization
Optical components
test and selection
SiPM program
radiation tolerance
and cooling program
Custom electronics
2023 ++
TDR readiness
EIC configuration
engineering, realistic PID
Beam test 3:
- Contingency:
- Performance assessment
- Component optimization
Optical components
refinement and
cost reduction study
(e.g. glass-skin mirror)
SiPM program
radiation tolerance
and cooling program
Custom sensors
So far on track with the program presented at EIC R&D committee on 09/19
Possible with 60 k$/y (dRICH) + 60 k$/y (SiPM) + 30 k$/y (readout) + personnel